## Cultura
CEFETRA HEART 365: CULTURA (PRIMETICS)
Vendor Query Schedule: Clarification and Qualification Requests |  |  |  | Technical/Product to check
# | Query Type | Query | Your Response
1 | Commercial | Cefetra would prefer to take a small number of Primetics GOLD licences during implementation, and pay the full 210 user perpetual licence cost near go live rather than at the start of Year 1. Similarly for the Progress OpenEdge third party licences. Please confirm: (a) you support starting with a smaller user pool during build and test phases, (b) the minimum count required for implementation activities, (c) the unit cost remains the same at the final 210 user purchase with no penalty for phased buy, (d) any volume discount lost if not bought up front, (e) can the full Progress OpenEdge amount be deferred to near go live as well. | Phased licence purchase: Yes, Primetics can support Cefetra starting with a smaller Primetics GOLD user pool during the build and test phases, with the full 210-user perpetual licence purchase made nearer go-live. We can also support the same principle for the Progress OpenEdge third-party licences. (a) Smaller user pool during build and test: Yes. A reduced licence pool can be used during implementation for the core project team, Primetics consultants, Cefetra SMEs, test users and any required background processing activity. (b) Minimum count required for implementation: The minimum implementation licence count will be agreed during mobilisation once the project team, test approach and environment plan are confirmed. As a guide, the implementation pool should cover named project users, key business testers, system administrators, interface/background processing users and Primetics access where required. (c) Unit cost at final 210-user purchase: Yes. The unit cost for the final 210-user perpetual licence purchase will remain consistent with the agreed commercial proposal, with no penalty for the phased purchase approach. (d) Volume discount impact: No volume discount will be lost provided the phased licence purchase and final 210-user commitment are agreed within the contract and Statement of Work. (e) Progress OpenEdge deferral: Yes, in principle the Progress OpenEdge licence amount can also be phased until nearer go-live, subject to Progress licensing rules and final supplier confirmation. Any minimum Progress licences required during build and test will be identified and agreed as part of the implementation environment plan.
2 | Commercial | Please confirm whether your quoted implementation fee includes Travel and Expenses for onsite delivery, or whether T and E is invoiced additionally. If additional, please provide: (a) a capped estimate (percentage of professional services or absolute pounds), (b) the methodology for tracking and approving T and E, (c) the approval process if T and E approaches the cap. | Travel and Expenses: Travel and expenses for onsite delivery are not included within the quoted implementation fee unless expressly stated in the final Statement of Work. Where onsite attendance is required, T&E will be charged at cost, with prior agreement on planned onsite activity. For budgetary control, Primetics proposes a capped T&E allowance 5% of professional services fees. All T&E will be tracked against the project, supported by receipts where applicable, and reviewed as part of regular project governance. If actual or forecast T&E approaches the agreed cap, Primetics will notify Cefetra in advance and no spend above the cap will be incurred without Cefetra’s written approval.
3 | Commercial | Microsoft D365 standard licences include only 2 environments (Production plus 1 Dev or Test). Please confirm all non production environments needed for your implementation methodology, including Test, UAT, Training, Pre Production, Performance or Integration test, and any Sandbox tier. For each, please state: (a) included in your quote, (b) separately costed (provide pounds figure), or (c) excluded (Cefetra to procure). Also provide per tier cost (Tier 1, 2, 3, 4) so we can model environment count flexibly. | Non-production environments: Primetics GOLD is not licensed or deployed using the Microsoft D365 environment model, and therefore the D365 Production + 1 Dev/Test limitation does not apply to the GOLD application. GOLD is deployed as a Progress OpenEdge application within the agreed Cefetra-hosted or customer-managed infrastructure model. Environment sizing and provisioning will be agreed during mobilisation with Cefetra IT and any hosting/infrastructure partner. GOLD can support the non-production environment model required for implementation, including Test, UAT, Training, Pre-Production, Performance/Integration Test and Sandbox where required. The GOLD deployment and configuration services are included in the Primetics implementation scope, but infrastructure/platform provisioning and any Microsoft D365 tier costs are excluded from the Primetics quote and should be modelled separately by Cefetra or the relevant platform provider.
4 | Commercial | Please confirm whether your fixed implementation cost includes development of reports and dashboards required to operate the new platform. Specifically: (a) which RFP listed reports are out of the box (no build), (b) which reports require build effort, (c) the build effort included in your fixed implementation fee, (d) day rate or cost if Cefetra requires additional reports beyond inclusion, (e) tooling assumed (Power BI Pro vs Premium vs Fabric capacity). | (a) The RFP-listed reporting areas are supported through standard GOLD enquiries, browser views, PETL, Excel/CSV extracts and Gold Digga reporting without bespoke report build. This includes contract enquiry and contract status reporting, daily trade and trading position views, purchase, sale, haulage and contract accrual reporting, financial accrual reporting by account, department, nominal and accounting period, invoice control, invoice preparation, supplier invoice control and invoice reconcile reporting. GOLD also provides standard visibility of stock on hand, free stock, stock movements, stock lots, inventory by location, storage area, ownership, quality status and product, as well as movement, fixing and transport status. Weighbridge, quality, analysis and claims visibility, self-bill and settlement support, audit, document, diary and workflow exception reporting, and mark-to-market, valuation and position-related reporting where configured are also available through the standard reporting toolset. (b) Reports requiring build effort: Reports that are Cefetra-specific in layout, calculation, pack format, management presentation, Power BI visual design, board pack styling, external distribution format, or that combine GOLD data with data from the chosen finance ledger or other third-party systems may require report-build or integration effort. Examples may include Cefetra-specific management packs, consolidated finance dashboards, bespoke Power BI dashboards, sustainability/carbon reporting formats, broker reconciliation dashboards, or any report requiring new calculated logic not already present in GOLD. (c) Build effort included in the fixed implementation fee: The fixed implementation fee includes configuration and deployment of the standard GOLD reporting set needed to operate the in-scope GOLD processes, including standard enquiries, standard extracts and agreed Gold Digga outputs within the implementation scope. Any specific report-build allowance, including number of bespoke reports or dashboards, should be documented in the final Statement of Work so both parties have a clear baseline. (d) Cost for additional reports: Additional reports requested beyond the agreed included scope would be handled through normal change control. Additional report-build work would be charged at the agreed professional services day rate of £1,260 per day, unless otherwise agreed in the final commercial schedule. (e) Tooling assumed: The Primetics proposal assumes use of native GOLD enquiries, browser extracts, Gold Digga reporting and PETL where required to expose structured datasets for downstream reporting. Where Cefetra wishes to consume GOLD data in Power BI, the required Microsoft licensing model — Power BI Pro, Power BI Premium, Fabric capacity or any equivalent Microsoft platform licensing — is assumed to be provided by Cefetra or its Microsoft/platform partner and is not included within the Primetics GOLD licence cost.
5 | Commercial | RFP Section 6.1 mandates per integration costing. Please provide: (a) how many integrations are included in your fixed fee, (b) per integration complexity classification (simple, medium, complex), (c) per integration cost in pounds for each complexity, (d) rate if Cefetra adds additional integrations post contract, (e) what triggers a complexity reclassification mid delivery. | Integration Costings: a) Integrations include TSS, CDS type integrations for customs and shipping declaration. Gold to Finance system integration, G/L finanical posting inclusing accuals. Provision for Market Price Import and nominated Exchange Rate feed where available, and agreed within the Statement of Works, including agreement on the source/service provider. [The source data may be subject to an external fee to the provider. This fee would be for the Cefetra account.] 3 Integrations are indicated within the projected day count to cover the above key areas. b) Complex - Financial Solution, exchange of P/L data, G/L Entries, Credit Information e.g. integration to D365,Business Central,Sage. Medium - TSS/CDS, Simple - market price/exchange rate API utilisation. c) The submitted scope includes an allowance of 50 days / £63,000 for in-scope integrations. If additional integrations are required, a simple file/API interface would typically range from £2.5k–£10k, medium £10k to £20k while a more complex interface involving detailed data mapping, error handling, testing, third-party coordination or less mature APIs would typically range from £20k–£60k per interface.Project Consultancy Rate as determined in the commercial schedule. d) Project Consultancy Rate post agreement on the scope and any specific statement of works for the integration. e) A re-classification is represented where there is a material divergence from a documented API that is then mitigated via the Primetics team, such as incorporation of new workflow, data constructs, failsafe solutions, or the extension of an agreed scope that requires rework, database modification, more complex engineering or algorithm. A complexity recalculation can also occur where a solution is found to be achievable at a reduced effort, following analysis by the team.
6 | Commercial | Please confirm what data migration tooling is included in your fixed fee: (a) source to staging ETL build, (b) data cleansing tools, (c) reconciliation and validation tooling, (d) cutover automation. Please also state explicit out of scope items. | Data migration: The submitted scope includes the use of Gold import templates, ( inc. trading partners, addresses, contracts, stocks, profiles) data-load support, validation support and cutover rehearsal activity for the agreed in-scope migration dataset. Additional migration objects would typically range from £10k–£20k, while more complex transformation, reconciliation or larger historic migration scope and use of staging or similar approaches could range from £30k–£50k+, depending on data quality, source-system access and validation requirements. b) Data cleansing tools would be for Cefetra to adopt in conjunction with the import requirements and data formats. c) Importation of migrated data and subsequent validation will be for the Cefetra and Primetics team to agree, following familarisation of both parties with current datasets. d) Cut Over automation is not specified within the current proposal, works required can be agreed in alighment with point c). Typically a business will look at current balances and inventory levels, for contracts this can represent the contract current balances and open bookings, imports do exist for bookings and pendinng weights. Typically full invoice reconstruction and G/L/VAT entries are not input. Where Document Store us integrated, the upload capabilities provide for migration of documents such as previously issued Invoices, claims that can be indexed against the Trading Partners and tagged with previous reference numbering.
7 | Commercial | Slide 20 shows Year 2 to Year 5 support compounding at 4 percent RPI (161.4k, 167.9k, 174.5k, 181.5k). Please confirm: (a) the 4 percent is contractual cap or estimate, (b) index used (UK RPI, Cultura discretion), (c) what happens if RPI exceeds 4 percent in any year, (d) can Cefetra fix the rate at contract signature. | Annual maintenance indexation: The 4% shown on Slide 20 is an illustrative forecasting assumption used for TCO modelling, not a confirmed contractual cap unless agreed as such in the final contract. The slide notes that a 4% RPI increment has been applied for years 2 to 10 for forecasting purposes. (a) Contractual cap or estimate: The 4% is currently an estimate for modelling purposes. Any contractual cap would need to be agreed and documented in the final commercial terms. (b) Index used: The assumption is based on UK RPI (ONS). Final indexation wording, including whether UK RPI or another agreed index is used, will be confirmed in the contract. (c) If RPI exceeds 4%: If no cap is agreed, annual maintenance would increase in line with the agreed contractual indexation mechanism. If Cefetra wishes to cap the annual increase on a min/max basis, Primetics is open to agreeing this in the final commercial schedule. (d) Fixed rate at contract signature: Yes, Cefetra and Primetics can agree a fixed annual support increase or capped indexation rate at contract signature, subject to final commercial agreement.
8 | Commercial | Please confirm: (a) validity period of pricing in your RFP response, (b) re pricing triggers, (c) lock in mechanism at contract signature. | Pricing validity and lock-in: The pricing submitted in our RFP response is provided on the basis of the stated scope, assumptions and commercial model set out in the proposal. Pricing is subject to final scoping and agreement of the Statement of Work, as noted in the submission. (a) Validity period: The pricing in the RFP response is valid for 90 days from submission date, subject to no material change in scope, user numbers, third-party licence terms, delivery timeline or implementation assumptions. (b) Re-pricing triggers: Re-pricing may be required where there is a material change to the agreed scope or assumptions, including changes to user numbers, modules, integrations, customisations, environments, reporting requirements, data migration scope, delivery timescales, third-party licence costs, hosting/infrastructure assumptions, travel/on-site requirements, or any additional work requested beyond the agreed Statement of Work. (c) Lock-in mechanism at contract signature: Pricing will be locked in at contract signature through the agreed Statement of Work and commercial schedule. Once signed, changes to price would only arise through the agreed change-control process or where third-party supplier costs change outside Primetics’ control and are treated as pass-through costs under the contract.
9 | Commercial | Please confirm whether Microsoft Fabric capacity, Azure consumption, AWS, or any other cloud cost is included in your quote or separately invoiced. If included, state assumed capacity (Fabric F SKU, Azure DTU etc). | Cloud and platform consumption costs: Microsoft Fabric capacity, Azure consumption, AWS consumption, D365 environment costs or any other cloud/platform consumption charges are not included in the Primetics quote unless expressly stated in the final Statement of Work. The Primetics proposal is based on GOLD being deployed within the agreed Cefetra-managed or customer-hosted infrastructure model. As set out in our submission, Primetics typically supplies the GOLD application and Progress OpenEdge solution, with the hosting environment, infrastructure, backup, resilience and cloud consumption model determined and controlled by Cefetra IT or its chosen hosting/platform partner. Therefore, no Microsoft Fabric F SKU, Azure DTU/vCore, AWS instance size, storage tier or cloud consumption capacity has been assumed within the Primetics commercial quote. Where Cefetra wishes to use Microsoft Fabric, Power BI, Azure, AWS or another cloud platform for reporting, hosting, integration, data storage or analytics, those costs should be modelled and procured separately by Cefetra or the relevant platform provider. Primetics will support sizing discussions and integration design during mobilisation, including any requirements for GOLD, PETL, reporting feeds, interfaces, backups or non-production environments, but the underlying cloud/platform consumption costs are excluded from the Primetics licence and implementation pricing.
10 | Commercial | Please review the Cost Comparison and confirm every figure in your column reconciles to your RFP submission: (a) per user per year rates, (b) Year 1 and Year 2 plus quantities, (c) implementation flat fee, (d) environment costs, (e) support figures, (f) 5 year TCO. Flag any discrepancy from your own commercial proposal so the data can be corrected before Cefetra commercial scoring. | Commercial model clarification: Primetics does not offer GOLD as a SaaS subscription product. Our submitted proposal is based on a perpetual licence model for the GOLD application, with annual maintenance and support. Therefore, any “per user per year” figures in the Cost Comparison should not be treated as the commercial basis of our offer. The correct commercial basis is: GOLD perpetual licence: one-off licence cost based on the agreed user quantity Progress OpenEdge third-party licences: one-off third-party licence cost based on required user / processing quantity Implementation services: estimated project delivery fee for the agreed implementation scope Annual maintenance and support: recurring annual charge for support and maintenance of the GOLD application and associated products Hosting / cloud / infrastructure: excluded from the Primetics quote unless expressly agreed separately
11 | Commercial | Your implementation cost is 176,400 pounds (140 days at 1,260 per day). Please confirm: (a) T and E included or separately invoiced, (b) onsite vs remote delivery split, (c) reporting development effort included, (d) any pass through costs (Azure or AWS) for Progress OpenEdge hosting. | Implementation cost clarification: Our submitted implementation cost is £176,400, based on 140 professional services days at £1,260 per day, covering the agreed GOLD application deployment, database deployment, configuration, installation, training, integrations, transactional documentation/branding and go-live support within the stated RFP scope. (a) Travel and Expenses: Travel and expenses are not included in the £176,400 implementation fee unless expressly agreed in the final Statement of Work. Where onsite attendance is required, T&E would be charged separately at cost, subject to prior agreement, project governance review and any agreed cap. (b) Onsite vs remote delivery split: The implementation fee assumes a blended delivery model using both remote and onsite activity. The precise onsite/remote split will be agreed during mobilisation and will depend on workshop needs, testing approach, training plan, integration activity, cutover and go-live support requirements. Our normal approach is to use onsite time where it adds the most value, particularly discovery, key design sessions, process playback, UAT support, cutover readiness and go-live/hypercare. (c) Reporting development effort: The implementation fee includes provision and configuration of the standard GOLD reporting set required to operate the in-scope GOLD processes, including standard enquiries, browser views, Excel/CSV extracts (PETL) and agreed Gold Digga outputs. Bespoke Cefetra-specific reports, dashboards, Power BI visualisations, combined reports using non-GOLD data, or new calculated reporting logic beyond the agreed scope would be handled through the Statement of Work or change control. (d) Pass-through costs for Progress OpenEdge hosting: The proposal does not include Azure, AWS, Microsoft Fabric, D365 environment costs, hosting infrastructure, cloud consumption, storage, backup or other platform pass-through costs for hosting Progress OpenEdge. GOLD is proposed as a Progress OpenEdge application deployed within the agreed Cefetra-managed or customer-hosted infrastructure model. Any Azure, AWS or other hosting/cloud costs would be procured and paid by Cefetra or its chosen hosting/platform partner, unless expressly agreed otherwise in the final contract.
12 | Commercial | Please quantify likely additional implementation cost ranges for: integrations, reporting, BI tooling, document layouts, data migration, customisations, workflow approvals, and automation. Cefetra needs indicative ranges to bound change-budget exposure. | The submitted implementation fee of £176,400 includes 140 professional services days at £1,260 per day, including an allowance of 50 days / £63,000 for integrations, plus GOLD deployment, database deployment, configuration, installation, training, transactional documentation/branding and go-live support within the agreed RFP scope. The ranges below are indicative only for work beyond the agreed fixed implementation scope and would be confirmed through discovery, Statement of Work definition and formal change control. Integrations: The submitted scope includes an allowance of 50 days / £63,000 for in-scope integrations. If additional integrations are required, a simple file/API interface would typically range from £2.5k–£10k, medium £10k to £20k while a more complex interface involving detailed data mapping, error handling, testing, third-party coordination or less mature APIs would typically range from £20k–£60k per interface. Reporting: Standard GOLD enquiries, browser views, Excel/CSV extracts and agreed Gold Digga outputs are included within the implementation scope. Additional reports beyond the agreed scope would typically range from £1.5k–£3k for a simple report and £5k–£10k for a more complex report pack, depending on layout, calculations, scheduling, distribution and approval requirements. BI tooling: The proposal assumes use of GOLD native reporting, Gold Digga and PETL-supported data exposure where agreed. Microsoft Power BI, Fabric or other BI platform licensing is excluded. Additional BI dashboard or semantic-layer build activity would typically range from £5k–£10k+, depending on the number of dashboards, data sources, data model complexity and whether non-GOLD data must be combined. Document layouts: Transactional documentation and branding for agreed standard outputs are included in the submitted scope. Additional document layouts or more complex variants would typically range from £1.5k–£3k per straightforward layout and £5k–£10k+ for complex conditional layouts, multi-entity variants, multi-language variants or new document types. Data migration: The submitted scope includes GOLD import templates, data-load support, validation support and cutover rehearsal activity for the agreed in-scope migration dataset. Additional migration objects would typically range from £10k–£20k, while more complex transformation, reconciliation or larger historic migration scope could range from £30k–£50k+, depending on data quality, source-system access and validation requirements. Customisations: Any customisations included in the final fixed implementation scope will be documented in the Statement of Work. Additional customisations would typically range from £5k–£10k for small changes, £15k–£25k for medium functional extensions, and £50k+ for new modules or complex bespoke capability, depending on functional complexity, testing effort and upgrade/support considerations. Workflow approvals: Standard GOLD workflow, status and authorisation configuration for the agreed processes is included where in scope. Additional approval flows would typically range from £1.5k–£5k, while more complex multi-stage approval logic, exception routing or cross-system approval requirements could range from £15k–£35k+. Automation: Standard task scheduling, import/export routines and agreed process automation are included where in scope. Additional automation would typically range from £5k–£10k for simple scheduled automation and £15k–£50k+ for event-driven automation, complex exception handling, external triggers or multi-system automation. These figures are provided to help Cefetra bound potential change-budget exposure. They are indicative only and not a substitute for scoped estimates. Final costs would depend on agreed requirements, design complexity, third-party availability, test effort, data quality, security requirements and whether the change is delivered as configuration, report build, integration or custom development. All additional work would be managed through the agreed change-control process before any cost is incurred.
13 | Architecture | Please list all Microsoft Power Platform dependencies (Power Apps, Power Automate, Power BI Premium, Fabric, Dataverse) required for your solution and confirm whether the associated capacity licences are: (a) included in your quote, (b) separately costed (provide figure), or (c) Cefetra responsibility to procure. | There are no Microsoft Power Platform dependencies and no capacity licences included in the commercial proposal. It is for Cefetra to to determine their requirements and needs in terms of Microsoft associated products. Typical Gold customers will utilise a combination of the business focused enquiry screens utilised by users, Gold - Digga reporting, PETL , with Power Bi utilised frequently for further dashboarding and presentation. PETL transformed data is used directly or a further business defined semantic model generated for use with reporting tools as the business scales.
14 | Architecture | You provide Primetics GOLD CTRM as a standalone solution. Cefetra requires both CTRM and ERP. Please confirm: (a) which ERP solutions have you successfully integrated Primetics GOLD with (e.g. D365 F and SCM, SAP, Sage, Oracle, Business Central), (b) for D365 F and SCM specifically, provide reference architecture for the integration, (c) integration build effort, (d) which ERP would you recommend for Cefetra and why, (e) Cefetra needs to procure D365 separately and we estimate around 627,600 pounds 5 year Microsoft licence cost. Please confirm this is realistic. | The Gold application delivers the core CTRM and SCM functionality by managing trades, contracts, shipping, risk, logistics, pricing, actualisation, inventory movements, invoice generation and distribution and operational supply-chain processes. It prepares finance-ready outputs, including customer and supplier invoices with the appropriate G/L and tax breakdown, and hands off controlled postings into the Finance application/ERP. The handoff can include accruals, inventory valuation and accounting-ready journals, while the Finance ERP remains responsible for AP, AR, G/L, tax, statutory finance and statutory financial reporting. Primetics preferences are for API driven integration to the preferred finance solution with secure authentication. Deliveries to date include Filedrop, SOAP / XML, RestAPI, MS WSDL (e.g MS GP), direct write - staging tables. (Openaccounts). Example integrations include Sage, JD Edwards, NetSuite, Opera, Open Accounts, Business Central. The development team are internal and work with documented API to produce the robust integrations necessary for the transactional flow.
15 | Architecture | What finance platform, who implements it, who owns reconciliation, will this work with Microsoft D365. Please provide a comprehensive response covering: (a) recommended finance platform (D365 F &O SCM, Business Central, other), (b) integration architecture, (c) ownership of reconciliation between CTRM and finance, (d) precedents of similar Cefetra scale integrations delivered. | The Cefetra business will procure and implement the Finance solution using internal resources in conjunction with the solution supplier. Primetics will provide consultancy and business analysis support to establish the integration requirements, agree operational data flow mapping, role and function controls, and prepare the statement of works for agreement between all parties. Primetics will instruct the Primetics development team in pursuance of the works. Primetics would seek to use RestAPI where supported, in conjunction with platform specifics such as OData. It is expected that SME's from Cefetra finance team and the finance solution provider form the team and prepare all necessary testing schedules , specification for hand offs, and identify control gates for reconcilation. Typical procedures for reconcilation reside with Finance with robust control gates for data mappings such as G/L code, Tax coding applied at time of update. Frequent installations apply Batch referencing for direct reporting of data transferred and allowing for historic enquiry and auditing.
16 | Architecture | Primetics GOLD runs on Progress OpenEdge. Please confirm: (a) Progress OpenEdge skills market availability in UK, (b) Cefetra IT support implications (will Cefetra need Progress skilled DBAs), (c) Progress vendor support directly, (d) cloud hosting options for OpenEdge or is on premise required. | a) Progress OpenEdge skills market is existent with many large organisations operating with Progress at their core. Primetics recently recruited two new senior developers and within our Trainee scheme bring all new recruits through the Progress training schedule. It should be noted that as part of CSI ( Constellation Software ), there are additional businesses utilsing Progress and collaborations and check ins are undertaken. Within our RFD responses it will be seen that our development team are not just OpenEdge developers. We work with different technology stacks based on project needs and requirements, with the Gold web and app based applications providing our digital platform approach for Role focused capabilities. b) Progress OpenEdge is a proven, low-risk database platform for business-critical applications because it has been designed to run reliably as part of the application environment, rather than requiring customers to build a large database administration capability around it. It supports high availability, replication, monitoring, security and performance management, while allowing operational teams to run the system with relatively limited internal DBA overhead. For many of our customers, the value is not that OpenEdge is the most utilised database technology; it is that it is robust, scaleable, efficient, mature and well understood in production. Primetics will support initial configuration for optimisation and back up, configuration for before and after imaging for provision of safe roll back and transactional security. Primetics offer DB monitoring as a service including telemetry tooling. c) Progress licences do provide for maintenance. The maintenance is provided via the vendor ( Primetics ) and not direct. d) Gold and Document Store can be hosted on premises or a cloud tenant in Azure or AWS.
17 | Architecture | Is CRM integration included within scope? Please confirm: (a) the recommended ownership split between CRM (relationship), CTRM (trade execution), and F&SCM (financial settlement), (b) named CRM platforms you have integrated with at production scale, (c) integration build effort, (d) data ownership and synchronisation pattern. | A standard Gold installation will cover the management of Master data for Trading Partners ( accounts / counterparties ), Addresses, Contacts, Terms and Profiling Data. Gold will support management of "Prospect" accounts with facility to capture information related to the Prospect, Calls, Diary, Sample Data, Address, Key Contacts, Profiling Information ( e.g. Cropping, Farm Size, Assurance and Quality References, Compliance Data ). The Integrated Document Store will support upload of documentation for the Prospects and the Trading Partners ensuring all information is captured. Campaigns and capture of Cropping records is also a feature. The Gold WebCRM solution provides access for users to manage accounts and update details, view transactional histories, record conversations and calls and upload documents. Users utilising CRM screens in Gold are able to view transactional data for the customers and suppliers to support proactive conversations and manage core address book data. User Roles and Security control what the user has access to. Typical Gold deployments will push Master data to peripheral systems and separate CRM solutions are typically not required. The Primetics team can discuss further should an integration become a mandatory requirement.
18 | Functional | What finance platform? Who implements it? Who owns reconciliation? will this work with Microsoft? F&SCM or BC? | The Cefetra business will procure and implement the Finance solution using internal resources in conjunction with the solution supplier. Primetics will provide consultancy and business analysis support to establish the integration requirements, agree operational data flow mapping and prepare the statement of works for agreement between all parties. Primetics will instruct the Primetics development team in pursuance of the works. Primetics would seek to use RestAPI where supported, in conjunction with platform specifics such as OData. It is expected that SME's from Cefetra finance team and the finance solution provider form the team and prepare all necessary testing schedules and identify control gates for reconcilation. Typical procedures for reconcilation reside with Finance with robust control gates for data mappings such as G/L code, Tax coding applied at time of update. Frequent installations apply Batch referencing for direct reporting of data transferred and allowing for historic enquiry and auditing.
19 | Functional | estimated customisation volume, upgrade implications,
20 | Functional | Please restate, for each requirement classified as GAP or CUSTOMISATION in your Appendix A response: (a) priced gap cost, (b) configuration only alternative if available, (c) upgrade safety and ALM implications, (d) long term maintenance approach.
21 | Functional | Estimated customisation volume, upgrade implications. Please quantify: (a) GAP rows from your Appendix A response, (b) typical customisation effort to close those gaps in days or pounds, (c) upgrade safety strategy for Primetics GOLD when new versions are released, (d) ongoing maintenance burden.
22 | Functional | How are exposure calculations managed across commodity, location, counterparty, currency, and quality specifications? Please confirm configurability of dimensions, real-time vs batch calculation, and reporting output formats.
23 | Functional | Are market data integrations (price feeds, futures exchange data, FX rates) included within scope and budget? Please confirm: (a) named market data providers integrated (Refinitiv, Bloomberg, ICE, etc), (b) per-integration cost, (c) ongoing subscription cost responsibility (Cefetra-paid vs vendor-included), (d) typical Cefetra-scale market data spend.
24 | Functional | What predefined commodity trading reports are included out of the box? Please map them against the HEART 365 reporting requirements and identify which Cefetra requirements are covered standard, which require configuration, and which require build.
25 | Scope | Does the contract module allow wider use of contracts beyond trade contracts, including NDAs, leases of buildings, and other agreements with key-date reminder management? Please confirm capability, configuration effort, and any licensing implications.
26 | Scope | Are all logistics integrations included within scope, including weighbridge, hauliers (e.g. PodFather), storage providers (ports), and customer-facing logistics? Please confirm per-integration cost, named precedents, and Cefetra-specific scope assumptions.
27 | Clarification | Please clarify the expected operational support model after go-live and confirm what level of Cefetra technical capability is assumed post-implementation: (a) Cefetra-side roles required (DBA, application admin, integration specialist), (b) hours per role per month assumed, (c) skills market availability for those roles, (d) handover and training approach.
28 | Clarification | Please provide examples of nice-to-have versus must-have decisions typically encountered on comparable engagements at Cefetra scale and complexity, including how those decisions are governed during delivery.
29 | Clarification | Please provide a consolidated scope statement covering: included services and integrations, excluded services, assumed services, and future optional services. Present as a single auditable list to support change-control governance.
30 | Risk | Please confirm: (a) percentage of total delivery resource UK or EU based, (b) percentage offshore, (c) for offshore, which workstreams (Build, Test, Support), (d) named individuals at key roles or role level commitments only.
31 | Risk | Please explain the long-term architectural vision for your platform over the next 5 to 10 years. How will the platform evolve alongside AI, automation, analytics, workflow orchestration, and enterprise integration trends? Confirm investment commitments and end-of-life policy.
32 | Legal | Please confirm IP ownership treatment of: (a) configurations, (b) custom extensions developed under this engagement, (c) integration code, (d) reports and dashboards built. | IP ownership: Primetics’ standard position is that the GOLD application, underlying product code, product framework, tools, libraries, methodologies, templates, utilities, pre-existing IP and any generic enhancements to the GOLD platform remain the intellectual property of Primetics / Cultura Technologies. Cefetra will receive the contractual rights to use the configured GOLD solution under the agreed licence and support terms. (a) Configurations: Cefetra-specific configuration created during the engagement will be available for Cefetra’s use within its licensed GOLD environment. The underlying configuration tools, product structures, templates and standard GOLD capability remain Primetics IP, while the Cefetra-specific configuration data and business settings are available for Cefetra’s operational use under the licence. (b) Custom extensions: Custom extensions developed specifically for Cefetra will be governed by the final contract and Statement of Work. Primetics’ proposed position is that Cefetra will have a perpetual right to use the custom extension within its licensed GOLD environment, while Primetics retains ownership of the underlying codebase, development framework and reusable components. Where a development is genuinely Cefetra-specific and contains Cefetra confidential business rules, those elements will be protected under the confidentiality provisions. (c) Integration code: Integration code developed using Primetics standard integration patterns, tools, APIs, import/export routines or middleware connectors remains Primetics IP, with Cefetra receiving the right to use the integration for the agreed purpose within its licensed environment. Any third-party integration components, APIs, middleware or platform services remain subject to the relevant third-party licence terms. (d) Reports and dashboards: Standard GOLD enquiries, Gold Digga reports, PETL outputs and reporting tools remain Primetics IP. Cefetra-specific report definitions, layouts, parameters, schedules and dashboards built for the project will be available for Cefetra’s use within the agreed solution. Where reports or dashboards are built in third-party tooling such as Power BI or Fabric, ownership and use will also be subject to the applicable Microsoft or 3rd party platform licensing terms. Final IP wording will be confirmed in the contract, but the intended principle is that Cefetra owns its data and receives the right to use the configured/customised solution for its business, while Primetics retains ownership of the GOLD product, framework, reusable components and underlying software IP.
33 | Legal | Please confirm: (a) duration of transition support, (b) cost model (included, T and M, or fixed), (c) deliverables (documentation, code, data, environment access), (d) any tie in clauses. | Transition support: Transition and exit support will be agreed in the final contract and Statement of Work, but our standard position is that Primetics will provide reasonable transition assistance to support Cefetra in moving to another solution or support model if required. This would be delivered in a controlled way to protect business continuity, data integrity, security and confidentiality. (a) Duration of transition support: The duration would be agreed as part of the final contractual terms. As a working assumption, transition support would normally be provided for an agreed period following notice of termination or exit planning, sufficient to support data extraction, knowledge transfer, documentation handover and orderly transition activity. The exact duration should be confirmed in the contract. (b) Cost model: Transition support is not assumed to be included as an unlimited service within the standard annual maintenance fee. Reasonable application support continues under the active maintenance agreement, but specific exit or transition project activity would normally be charged on a time-and-materials basis at the agreed professional services day rate, unless a fixed transition package is agreed in the final contract. (c) Deliverables: Transition deliverables would typically include agreed system documentation, configuration information, interface specifications, data extract support, reporting/data dictionary support where available, handover sessions, assistance with environment access arrangements, and support for controlled export of Cefetra-owned data. Cefetra would retain ownership of its business data. Product source code, GOLD underlying IP, proprietary tools, reusable components and Primetics/Cultura development frameworks would not be transferred unless expressly agreed in writing. (d) Tie-in clauses: Primetics does not intend to rely on unreasonable operational tie-in clauses. Cefetra’s continued use of GOLD would remain subject to the agreed licence, maintenance and third-party licensing terms, including Progress OpenEdge and any other applicable third-party components. Any termination, notice period, continued access, data extraction, support continuation or exit assistance provisions should be clearly documented in the final contract so Cefetra has a controlled and practical exit route.
Total queries: 33 ¦ Please complete every query in the "Your Response" column ¦ Return to: gill@cefetra.co.uk copying beveridge@cefetra.co.uk